## Slide 1
UNION BANK OF INDIA –
CLOUD BASED EMAIL SOLUTION
- Project roll out approach
May 2021
SIFY is a leading integrated ICT player in India, helping customers to achieve their digital ambition through cloud@core products and services,
built on its world class Data Centers, Cloud & Network assets and wide portfolio of professional and digital services

## Slide 2: AGENDA
Sify Technologies – Introduction
Our Understanding of UBI Requirements
Proposed Architecture & Solution
Project Schedule, Risks and Escalation matrix
2

## Slide 3
Sify Technologies – Introduction

## Slide 4: SIFY’S JOURNEY: 25 YEARS OF TRANSFORMATION
Sify 1.0
Sify 2.0
Sify 3.0
Sify 3.0+
Sify 4.0
CONSUMER FACING ISP
Launch of MPLS & Data Center services in India
First private ISP in India
Launch of Enterprise Cloud services
DIGITAL ICT SERVICES PROVIDER
(cloud@core)
Launch of private and hybrid cloud services
DIGITAL TRANSFORMATION SERVICES PROVIDER
(digital@core)
SHIFT TO AN ENTERPRISE SERVICES COMPANY
TRANSFORMATION INTO ICT SERVICES COMPANY
Launch of end-to-end digital services
RELEVANCE
Products and Services always aligned to market trends and customer need
INVESTMENTS
Investments in line with market trend and strategic objectives
GROWTH
Consistent growth through investments and customer engagements
ACHIEVEMENTS
Recognized as a trend setter or leader in multiple lines of business
Consumer internet
Enterprise adoption of internet
Social and mobile on cloud
Emergence of cloud first
Relentless push to digital first

## Slide 5: SIFY ICT services KEY FACTS points
400+
Enterprise Cloud clients
70+
Private Cloud & DR clients
30+
CDN & Cloud Security clients
30+
IT Ops Transformation projects
500+
Datacenter services projects executed
300+
Datacenter Migration projects
80+
Platform Migration Projects
22K+
Managed Tickets per Month
100K+
Network Devices
91k+
Managed Mailbox
700+
DC, Cloud & Managed Service Team
CUSTOMERS
PROJECTS
VOLUME
5000+
Security Devices
100+
Certified Security Experts
7 Petabyte
  Managed Storage and Back-up
PEOPLE

## Slide 6: INTEGRATED ENGAGEMENTS: key references
HYBRID CLOUD LED
Managed Hosted/ PRIVATE CLOUD led​
Cloud Services led
Network services led
MANAGED services led

## Slide 7
Understanding of UBI Requirements

## Slide 8: Project Overview
OBJECTIVES
Migration of Exchange, Lotus- notes and Zimbra mailbox to cloud base mailbox
Enabling consolidated Office solutions across UBI, e-Andhra Bank & e-Corporation Bank
Training and end user awareness sessions
Set up Microsoft Office at HO, RO and ZO locations
Support and maintenance of the proposed solution for a period of 3 Years
REQUIREMENTS
Migration of 40000 mailboxes to Microsoft Office 365
Setting up integration with AD, ADFS to enable single sign on
End user awareness sessions on the new Microsoft Office 365 solution
Deploy Microsoft office at HO, RO and ZO locations
Helpdesk setup and deployment of One L2 and Four L1 resources at UBI Mumbai HQ for a period of 3 years
Support and maintenance of Microsoft Office 365 solution

## Slide 9: Implementation & Support-1/2
PLAN
Project Plan
Procurement initiation
Project Team deployment
N/W & Performance assessment
Setting up the required Migration Infra
Assigning Microsoft Office 365 licenses
Pre-migration activities
IMPLEMENTATION
AD integration through Trusts
AAD and ADFS deployment
Deploy Migration Tools
Tenant Configurations
Perform UAT & pilot migration
Perform end – end migration for all identified users
Deploy Microsoft Office 365 at HO, RO and ZO locations

## Slide 10: Implementation & Support-2/2
TRAINING & END USER ADOPTION PROGRAM
MS FastTrack engagement
Awareness sessions to users, using train the trainer method
Webcasts on the usage of Office applications
Onsite engineers training for deployments other than HO/RO/ZO locations
HELPDESK SUPPORT
Resource deployment (One- L2 and 4 - L1) & Helpdesk setup at HO, Mumbai
Determining client ticketing tool readiness for helpdesk setup
Setup helpdesk and continue engaging with support over the next 3 Years

## Slide 11
Architecture and Solution

## Slide 12: Proposed Target Architecture
Assumption: e-CB's current AAD/ADFS is scaled to support 50K users
Federated Identity with Password Hash sync as fallback authentication in the event of ADFS not reachable
Transient Trust relationships are setup across three forests and objects are synced to e-CB forest form other domains
AAD and ADFS is setup to support logins from all three forests (different Issuer Uri and Support Multidomain)
Web Application proxies will be leveraged for the internet bound traffic
Fully site-resilient and High Availability Setup across DC and DR datacenters for both ADFS (MZ) and WAP (DMZ)
AAD Connect redundancy on DC and DR through Staging

## Slide 13: Proposed Solution
  Office 365 with Federated Identity
  ATP as Email Hygiene and DLP for compliance
  Enterprise Security (EMS+E3) for designated individuals
  Unlimited Mailbox sizes
Cloud solution
  Existing Exchange Server 2016 hybrid will be used as SMTP Relay to send transactional emails from Application servers if any
SMTP Relay
  Sify suggest implementing a SIEM solution with associated storage for importing O365 audit logs. If not deploy a windows-based file server in DC or DR
Log Server
  Bank shall provide necessary hardware, OS and AV for deploying Migration Tools
Migration Tool

## Slide 14: Key Pre-requisites
AD Consolidation/Cross DC network access for setting up transient AD Trust relationships
Access to Active Directory setup across three forests
Access to all the messaging systems (Exchange/Lotus and Zimbra) across the three entities with permissions
Physical access to the project resources for UBI/e-Corp/e-Andhra Bank Datacentres
Hardware procurement and provisioning for deployment of Migration Setup (Tools)
Hardware procurement and Provisioning for AAD, ADFS as per scale/specification recommended by project team
Network components (Load Balancers) procurement/placement to meet the HA requirements
Identified SMEs from Messaging and AD Infrastructure across three entities
E-Corp tenant extension until the license import
Design discussion and policies feedback
Bandwidth enhancements based on assessment
Client (Office, Teams) deployments across locations, ahead of Migration
Identification and Consolidation (if necessary) of the local archives for the migration/conversion
Email hygiene policies and frameworks from the existing email-hygiene system – for ATP, DLP, AIP configurations

## Slide 15: Exclusions
AD
Consolidation
Client Deployments other than HO/ZO/RO (150) identified offices
Helpdesk physical presence beyond HO
Desktop Profile migration and domain joining
Existing Servers decommission and associated cleanup activities

## Slide 16: Assumptions
The Customer provides necessary access to the tenant and other Customer infra (AD and Messaging) to Sify project team during the project duration
Hardware, Windows Server Operating System, and Antivirus licenses for all the components (including the Audit log servers) will be provided by the customer
Customer will facilitate Network access, VPN connectivity and physical access to deploy the migration workstations into the server networks for carrying out the migration activities
Bank shall provide the Network components and necessary Bandwidth provisions for both migration activities as well as end users as per Sify/Microsoft recommendations
. Customer will provide the facilities for the Onsite Helpdesk resources to carry out their assigned functions
Customer will provide the hardware for the migration components
(VMs for migration tool installations and Migration workstations etc)
The current Email gateway solutions will go redundant, and EOP/ATP will be the email gateway (MX destination for all) after migration
Any changes to existing Active directory to support the proposed authentication flow (UPN changes, attribute additions etc) shall be owned by Bank
UBI will provide the necessary Lotus Notes Client Software and id file(s) for the purpose of the Lotus to Office 365 migration
Compute and Storage required for the audit logs will be provided by the customer and are not factored by Sify. Customer will also provide for the backup of audit logs
The customer will provide necessary network access and firewall changes to make the solution work
Ticketing tool shall be provided by Bank

## Slide 17
Project Schedule & Risks

## Slide 18: Project Phases

## Slide 19: Project Phases
Initiation
Planning
Execution
Control
Closure
Setting up the required hardware
Migration Setup
Assigning Office 365 licenses and pre-migration activities. UAT for specified users
Client deployments at RO/ZO
Pilot/UAT Migration.
Velocity Migration
End user training
Acceptance of PO
Project & implementation Team formation
Hardware readiness
Document high level risk and risk mitigation plan
Resource allocation
Project Kick-Off meeting
Development of project plan
Development of communication Plan for project stake holders
High level design document
Network assessment report
Review of actual achievement vs. planned
Measure Performance of the team.
Take corrective actions based on gaps identified
Respond to Customer concerns
Complete documentation
Handover Document and manuals
Obtain Acceptance of Project Deliverables
Hand over to support Team
Facilitate Closure
Collect Feedback
Document Lesson Learned

## Slide 20: Key Risks and Mitigation
Risk Factor | Risk Level | Mitigation Strategy
Inadequate involvement from UBI: Delay in clarifications / sign off from UBI will impact schedules | High | Timely response is really important to meet the schedules. UBI will appoint single point of contact from UBI to signoff / provide clarifications and Sify will be in continuous touch with the UBIs single point of contact
Network band width issues | High | UBI to resolve the bandwidth issues as recommended by Sify Team and if required increase the bandwidth if issue persists for a longer duration which is impacting the schedule
No timely response from the Client IT teams | High | The existing Messaging/AD SME’s time should be planned and booked well ahead of time. UBI help is required if any delays from the Client IT teams
Infra readiness – migration cannot be started until the required infrastructure on premise is made available to the team | High | Infra required for migration tool set up, AAD Connect, ADFS, WAP, Log Servers, SMTP/Hybrid Servers to be ready a week ahead of the Execution phase of the project
Network connectivity across entities is needed for unification of AD identities across forests | High | Client needs ensuring timely establishment of connectivity across entities and make necessary Active Directory Forest changes to enable such seamless connectivity a week ahead of the execution phase of the project
Helpdesk tool – In order to provide help desk assistance to each user as they are migrated to O365 and commence use of the new platform | High | Client needs setting up and providing migration project team access to help desk systems/ticketing tool by end of the pilot migration phase to enable helpdesk support for migrated users as they migrate and commence using O365
Uptime and Performance of existing on-prem email infrastructure – sluggish or poor performing on-prem email infrastructure limits the time window for migration, thereby reducing migration velocity directly impacting schedule | High | Client needs to ensure current: On-Prem infrastructure uptime and performance issues are mitigated immediately upon being notified by the delivery team Bandwidth for connectivity across locations and also to the O365 Cloud infrastructure is established in line with Delivery Team recommendations post network assessment and be ready one week prior to commencement of Execution Phase

## Slide 21: Key Risks and Mitigation
Risk Factor | Risk Level | Mitigation Strategy
Client readiness for office client installation – Client machines, and personnel across locations should be made available during execution phase to enable delivery team to install O365 client components on individual desktops else users may not be able to access their O365 mailboxes and content using desktop clients | High | Client needs to ensure personnel scheduled for migration are intimated to be available in office the day they are being migrated to O365. Client shall also ensure desktop of each of such personnel is switched on, accessible and functioning optimally the day they are being migrated Under instances where such personnel and/or their machines are optimally unavailable for such installation, delivery team shall perform such activity for the said user during a later date within schedule and personnel shall continue accessing O365 leveraging their web browsers to access Office On Web Application thin client Under such circumstance, client shall direct the personnel to log a helpdesk ticket to enable delivery team track all such pending client installations
Network readiness for remote installation of O365 Clients – for certain clients, delivery team may require installing O365 client suite remotely leveraging remote deployment tools – it is recommended to ensure optimal network bandwidth to such desktops to enable such remote installations | High | Client shall ensure each desktop has optimal network/internet connectivity to enable such remote installations – this shall enable delivery team to optimally get each client installed and O365 accessible in faster time
The helpdesk team of 1 Level 2 and 4 Level 1 resources at this time are deemed optimal to provide 24X7 O365 support to the entire bank userbase – however later, helpdesk ticket volumes may result in incremental, temporary/long term spike in support resources need | High | Delivery team shall regularly report ticket volumes by severity, priority and capacity utilized to provide such support – spikes when reported should enable delivery team to manage additional load via incremental staffing augmentation to the help desk – such changes may result in a change request

## Slide 22: Project Critical Success Factors
Critical Success Factor | Steps to achieve Critical Success Factors
Understanding of Scope, Deliverables | Involvement of Solution, Delivery, Implementation from day-1 in all key discussions, decision making with client team
Project scheduling | Ensure timely delivery of Infra hardware, Licenses and other activities
Timely validation, approval on HLD | Approved HLD, Identification of SPOC from client
Timely delivery of migration infrastructure | Client shall ensure proactively to have on prem migration infrastructure ready for the delivery team to commence and complete migration activities on time
Successful pilot migration sign off | Sify team shall strive to ensure timely and successful completion of pilot migrations as they shall indicate the velocity of migrations for the rest of the users. At the same time, Client shall ensure timely validation and sign off on the pilot migrations so delivery team can proceed with complete migration with greater confidence
Migration Schedule and Staff Communication | Client shall in advance publish to their personnel the migration schedule and readiness steps immediately as Sify team releases such information to ensure personnel and their desktops are proactively ready to undergo migration
Risk management | Risk register with perceived risks, risk mitigation strategy. Identification of key risks and work on them till mitigated
Support Transition | UBI helpdesk readiness for support phase

## Slide 23: Project Review & Documentation
Phase | Documentation
Initiation | Scope of work / deliverables, Signed Agreement, Validated BOM
Planning | Detailed project plan, High level design document covering the entire solution, Network assessment report
Execution | User awareness training /program details
Control | Updated project progress, Weekly Status Reports
Closure/Handover | Final documentation, and handover to support
Review Phase | Frequency
Project Progress Report | Weekly in Word/Excel/PDF format
Project Progress Review | Once a month
Steer-com review | To be decided
Project Review
Project Documentation during Project Life-cycle

## Slide 24: Communication Plan/Management
Project Manager would be the authorized to communicate regular communication such as status updates, seeking clarification, scheduling of meeting, risks, escalation etc.
Project Manager will send the necessary weekly status reports, project updates to the UBI designed team.
  Client to identify the SPOC / Project Owner to receive & respond to communication from Sify.
  Project Owner can reach out to Sify – PM and Others shared in the escalation matrix for any requirement / information / Clarification.

## Slide 25: Escalation matrix
Level of Escalation | Role / Name | Email id | Time after which escalation to be done to next level
Level 1 | Service Delivery manager (Rajesh) | menghani.rajesh@sifycorp.com (+91) 9867656780 | 1 day after no reply from team
Level 2 | Service Delivery Head (Sainarayan) | sainarayan.balasubramanian@sifycorp.com (+91) 8310936804 | 1 day after no reply from Level1
Level 3 | Sify Delivery Head (Subhasish) | subhasish.dhar@sifycorp.com (+91) 9620455000 | 2 days after no reply from Level2

## Slide 26
Thank you